## PG
Sr. no | Feedback | Category | Feedback date | Feedback shared date to SWT | Status | Remark | Action For SWT
1 | PG can initiate request for audit once the mandatory criteria are met, Add given questions that need to answer before initiating request |  | 2025-06-09 | 2025-06-10 | In-progress | Questions received on 11th Aug | At PG Level 1. Implementation Year of PG - (Dropdown option - Year 1, Year 2, Year 3 & Graduate) 2. Name of PG/Gin? 3. PG code? 3. State? 4. District? 5. Number of active farmers (growing cotton) for the season? 6. Whether the PG undergone any Previous 3rd Party Audit ? (Yes/ No) 7. If Yes, year of last audit conducted? 8. Weather valid certificate is available? (Ye/No) At the verification level: Ask below question while accepting the request 1. Type of Audit? (provide below dropdowns) a. Initial Audit b. Surveillance Audit c. Follow Up Audit d. Renewal Audit e. Surprise Audit
2 | PG level user can initiate the request for multiple PGs. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
3 | PG Name, PG Code, associated villages, farmer count, land details and total quantity will be visible to users |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
4 | Once the verification team will reject the request it will go to initial PG level user where the User reinitiate the request only once. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout | On later discussions it was decided that, once the request has been rejected then that PG can not initiate request again for that year | Check this points
5 | The system will record the actual user who initiated the application (even on behalf of someone else) and send notifications to the relevant account holder or designated recipient. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout | Single PG can be mapped to multiple users (PG coordinators) and they can initiate request from their account. Notification mail will be sent to concerned users | Check this points
6 | File upload and download options will be available at the PG level for supporting documentation. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
7 | Calendar date selection will be restricted to future dates, within the financial year (April to March). |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
8 | A full history log will be maintained for transparency- Timeline |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
9 | Each application must include a tentative initiation date. If this date is in the past, the system will mark the request as late |  | 2025-06-09 | 2025-06-10 | In-progress | Date received from verification team on 11th Aug (Requests initiated after 31st Aug will be marked as Late) | No action required for this year, form next year we will make provision for this
10 | Download and upload buttons will be provided for supporting documents. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
11 | The external verifier can issue one of the following: • Certificate of Eligibility • Critical Certificate |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
12 | A text box for comments will be available, especially for conditional/critical cases, to indicate gaps and the necessary corrective actions. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout
13 | Super Admins will have limited rights to modify PG details, if necessary, to improve scores or finalize records. |  | 2025-06-09 | 2025-06-10 | Completed Before Rollout |  | Please check what access given to super admin, as currently there is no any option for the same
14 | Show escalation timeframe in days instead of minutes |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout | Its applicable to superadmin only
15 | Add PG Name after district name. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
16 | Display dashboard year as “2025-26” which should be Restrict dashboard date pickers to 01-04-2025 through 31-03-2026. |  | 2025-07-11 | 2025-07-12 | Done
17 | Rename “External Verification” to “Certification Bodies” and “Reject Certificate” tab to “Reject Request” |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
18 | Internal users see actual request start date; external verification (certification bodies) see only their receipt date. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
19 | Disable timeline widget for certification body (External Verification) role. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
20 | After certification body accepts audit request, cc verification team and external verification team (certification bodies) can propose an audit date |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
21 | Rename Audit Date as “Proposed Audit Date”. | Revised Feedback | 2025-07-11 | 2025-07-12 | Done | Done "Proposed Audit Start Date" and "Proposed Audit End Date"
22 | “Eligible for Certification” and “Not Eligible for Certification” tabs at external level instead of Reject Certificate. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
23 | Provide option to external verification team actual audit start and end date. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
24 | Show both proposed and actual audit start/end dates on the request tab. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
25 | Remove validation on NA Status Remarks. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
26 | Replace slanted dropdowns with standard vertical dropdowns and add a searchable filter - for code of conduct searching |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
27 | Add certificate award conditions in eligibility criteria alongside equal to or less than 60% score rule. For major NCs conditions rule refer Akshay email (Code to Standard – Demo). | System Bug | 2025-07-11 | 2025-07-12 | Pending | Systeam bug | If score is less than or equal to 60% then currently request is getting rejected, it should not reject, it need to process asper defined flow. provide reject option at verification level to reject the request
28 | Make certificate upload optional (no block on moving forward). |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
29 | We need to add two flows in appeal committee. One is Internal verification team and external verification team. If internal verification team wants to share with external otherwise skip the external verification. (proceed after discussion). |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
30 | Two account one Auditor and other Certificate Issuer at the External level. | System Bug | 2025-07-11 | 2025-07-12 | Done
31 | Instead of every popup that displays PG villages and farmer counts, please add a direct “Export Farmer List” button. When external auditors click this button, it should immediately download an Excel file containing only the essential columns they require: Name, Farmer Code, Village, State, District, PG Name, Total Rainfed Land, Total Irrigated Land, Total Agricultural Land, Total Cotton Land, and Estimated Production. | Revised Feedback | 2025-07-15 | 2025-07-15 | In-progress | As per verification teams feedback on 11th Aug will remove the Farmer's Father's Name, Total Rainfed Land, and Total Irrigated Land column from the sheet | For CB Level- farmer details need to download with below columns only Farmer Name, Farmer Code, Village, State, District, PG Name, Total Agricultural Land, Total Cotton Land, and Estimated Production.
32 | Simultaneously, our internal users should retain the ability to export the full Post Sowing Details report for their PG. Their download must include every column of post sowing report. |  | 2025-07-15 | 2025-07-15 | In-progress | Post Sowing list yet to finalise | For Verification, farm & PG level complete post sowing format list need to download
33 | Any pending entries should be highlighted in red. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
34 | In the Audit Date section, both proposed and actual audit dates are needed, including start and end dates. |  | 2025-07-11 | 2025-07-12 | Completed Before Rollout
35 | Rename – Export code to “ Download codes” and import & update code to “Upload & Update Code” | Revised Feedback | 2025-07-28 | 2025-07-28 | In-progress | Already done as per last feedback. we will revise it as per new feedback received. Rename – Export code to “Download Tool” and import & update code to “Upload & Update Tool” | Rename – Download code to “Download Tool” and Upload & update code to “Upload & Update Tool”
36 | Filters like Brand, programme, Country, state, district, PG name on home page of all levels | New Feedback | 2025-07-28 | 2025-07-28 | Done | working on country and PG filter | Add country & PG filter
Comments From Verification team on 29th July
37 | Rename Proposed Audit date as "Proposed Audit Start Date" and "Proposed Audit End Date" | New Feedback | 2025-07-29 | 2025-07-31 | Done
38 | Provide click option on tab that when user click on FC, PC, NC etc tabs codes will filter as per clicked tab | New Feedback | 2025-07-29 | 2025-07-31 | Done |  | This need to work thru out the application for all users
39 | If CB wants to edit the proposed dates given by Verification team, then that can be done and this edited date will reflect as proposed date | New Feedback | 2025-07-29 | 2025-07-31 | Pending | Will provide option at CB level to edit the proposed date | Provide option to CB team to edit the propose date, and that will overwrite the proposed date given by verification team
40 | Once the CB make decision of Not eligible for certification or report submission it directly reaches to CC Verification team to review the report and Verification team need to upload the updated report, then PG need to review the report and confirm the report. Process flow is attached separately. Provide option for internal appeal committee "Reject Appeal" and if user click on this it will directly go next level by skipping external appeal committee | New Feedback | 2025-07-29 | 2025-07-31 | Done | Reject option has been provided
41 | Dropdown of compliance status is required in downloaded excel - offline report | New Feedback | 2025-07-29 | 2025-07-31 | Done
42 | Change the tab label from “Needs Compliance” to “Non-Compliance.” | New Feedback | 2025-07-29 | 2025-07-31 | Done
43 | Once the certificate is finalized and issued in the portal, the detailed audit report (Excel sheet) is no longer available for viewing. Provide option to download audit report even after completion of request | New Feedback | 2025-07-29 | 2025-07-31 | Done |  | Currently Farm, verification and CB team can download the audit report allow PG team also to download report after completion of request
44 | In the initial step, if the Producer Group uploads incorrect reports or documents, there is no provision to change or update the first-party audit report through either the Producer Group portal or the CC Farm portal. Provide option to CC farm team to review and edit option for first party audit submitted documents | New Feedback | 2025-07-29 | 2025-07-31 | Done | Farm team can overwrite the documents by upload
45 | In the 'View Request' tab, the first-party audit reports initially uploaded by the Producer Group are always visible. These reports are also accessible from the Certification Body (CB) portal. This should not be seen at CB. Hide "View Request" tab for Certification body and external appeal committee | New Feedback | 2025-07-29 | 2025-07-31 | Done
46 | There is no provision or option to delete an evidence file that has been uploaded during the report preparation stage, either from the CB portal or the CC Verification portal |  | 2025-07-29 | 2025-07-31 | Completed Before Rollout | CB/verification team can upload documents multiple time till the final submission from his level. No required to remove firstly uploaded file it will overwrite by newly uploaded file
47 | Change "season start date" and "season end date" with Season and Change Proposed date and proposed end date with Proposed audit start date and Proposed audit end date. Under the state name( eg .Maharashtra) change the season end date and make it as State name | System Bug | 2025-07-29 | 2025-07-31 | Done
48 | In all PGs farmer details are shown, but not sure from where it is sourced. Please clarify downloaded excel not matching with farmer and village count as shown on web | System Bug | 2025-07-29 | 2025-07-31 | Done | As its test data and its pooled from MEL PG master, after actual farmers sync both farmer as well as village count will match with exported data
49 | Why does the status show 'Pending' even after a user completes their assigned task? It continues to show as pending for all users until the certificate is issued. This need to be revised, |  | 2025-07-29 | 2025-07-31 | Completed Before Rollout | This is already done and we are highlighting pending request in "Pending" orange tab over request and "Completed" in green on certificate issued requests. As discussed for user understanding if action button is disabled in their account that means they have already taken action on that request. All users can already see the on which level request is pending by following "Currently Request Team"
50 | Before final submission of the proposed audit date there should be pop up question as are you sure want to submit? Ask question as "Do you want to submit ?" before submitting the proposed date by both levels | New Feedback | 2025-07-29 | 2025-07-31 | Done
51 | In the current system once the CB upload the report, the marks (Score) are visible to PG and Farm team. This should be visible only after the acceptance from the verification team. Apply validation check as till CC verification will accept the audit score should not visible to PG, CC Farm, appeal committee . | New Feedback | 2025-07-29 | 2025-07-31 | Done |  | Please check it, some time visible some time not visible, make sure till CC verification will accept the audit, score should not visible to PG, CC Farm, appeal committee.
52 | After selecting the eligible for certification, two options pop out, yes and yes with condition this should be revised based on the flow | New Feedback | 2025-07-29 | 2025-07-31 | Pending | Revised process has been received on 11th Aug, we will work on the same | After selecting eligible for certificate two options need to pop out, "Yes" and "Yes with Condition" Make provision at CB to provide conditional certificate
53 | When CB upload report, Online Audit report showing score "0" in individual requirement tab irrespective of NC,PC,FC or NA | System Bug | 2025-07-29 | 2025-07-31 | Done
54 | When reports are uploaded with any pending requirements entry, system is showing wrong pending status eg: if 4 criteria is pending when uploading the report ,the system should display 4/207 is pending where as not its showing 203/207 is pending. On home page for pending conduct calculation error is there please correct | System Bug | 2025-07-29 | 2025-07-31 | Done |  | Pending conduct is not reflecting properly, please check
55 | Audit compliance status need to make mandatory at CB level for uploading the audit report (except NA status). Apply check at CB upload audit that - Compliance status can not be blank except NA status. Show error while uploading and ask to update the status | New Feedback | 2025-07-29 | 2025-07-31 | Pending | Make compliance status and Compliance remark mandatory while uploading the report - provide error with clear message popup as "Compliance Status and Compliance Remark fileds are mandatory" | Make compliance status and Compliance remark mandatory while uploading the report at CB - provide error with clear message popup as "Compliance Status and Compliance Remark are mandatory"
56 | Highlight appealed questions - need highlight for both committee accounts even after first team have taken action | New Feedback | 2025-07-29 | 2025-07-31 | Done
57 | Pending conducts need to highlight same as per appealed codes | New Feedback | 2025-07-29 | 2025-07-31 | Done | Tab has been provided to sort the pending conducts
58 | PG Assessment Tool: - Assessment tool in the portal on exporting the report is not in accordance with the Assessment tool shared by Verification Team. (Observation attached separately in assessment tool sheet) | System Bug | 2025-07-29 | 2025-07-31 | In-progress | Received final update on 11th Aug | Please provide audit tool exactly same as provided
59 | At the CB-1 level, in the "Upload Files" tab, if we click on a particular code, the cursor does not indicate that we have clicked on the code. Previously, this was not happening, but now it is occurring. | New Feedback | 2025-08-13 | 2025-08-14 | Pending |  | Highlight the particular code on which user have clicked for uploading the file, also on which coded file have uploaded highlight with with green tab, so user can understand the files has been uploaded for this codes

## Gin
Sr. no | Feedback | Feedback by | Feedback date | Feedback shared date to SWT | Status | Remark
1 | Process flow will remain dynamic as ( Supply chain – Verification team – Certification Body – Verification team) / (Ginner- supply chain-verification -certification-verification) | Verification team | 2025-07-28 | 2025-07-28 | In-progress
2 | The certification body will have 2 accounts as one for submitting the audit report and another for certification | Verification team | 2025-07-28 | 2025-07-28 | In-progress
3 | User can be mapped to multiple Gins in case of supply chain team initiating audit, / one user per ginner in case of ginner initiating audit request (Based on management decision) | Verification team | 2025-07-28 | 2025-07-28 | In-progress
4 | Separate tab modules will be generated for PG and Gin audit on the same platform, and escalation will also be separate | Verification team | 2025-07-28 | 2025-07-28 | In-progress
5 | Appeal can be redirected to the External Appeal Committee | Verification team | 2025-07-28 | 2025-07-28 | In-progress
6 | Filter option needs to be provide on the home page for sorting/ searching of Audit requests | Verification team | 2025-07-28 | 2025-07-28 | In-progress

## PG Assessment Tool FB (hidden)
Sr. No. | Feedback on Assessmnet Tool
1 | Needs Compliance (NC) should be change with Non compliance(NC)
2 | Change the term Code in the assessment tool
3 | there is a section called Category, don’t understand this. Change the term category , in the assessment tool
4 | Remove method of verification column
5 | Dropdown option is need to provided in compliance status
6 | It was found that the audit observations entered by the CB do not match when it was downloaded at the CB level/ verification level , the system is automatically populating the compliance remarks based on the predefined compliance definitions.
7 | Change title Question Description to Standard Requirements
8 | Clauses of Conduct is not required
9 | Major standard requirements are not displayed as per the requested assessment tool by verification team
10 | Farm size column is not showing in the report where as it was present in the assessment tool requested by Verification team
11 | Score column is not available
12 | Guidance on requirement is not available
13 | Group column is not available
14 | Initial report titled compliance remark changed to "compliance status" while downloading, when download again "compliance status" term is changed in to "selected option "
15 | After downloading the filled uploaded report ,Title bar is showing ID,Code ,question which is not matching initial report