## VTS Dashboard - ICCC
Sr No | Observations | Sub Observations | Recommandations | Description | Status(Done/Pending) | Expected closing date
1 | Observation 1: |  | 1. Enhance Real-Time Vehicle Status Visualization | The current dashboard fails to accurately indicate vehicles that are idle or parked. By integrating dynamic GPS telemetry (per vehicle based route uncovered shown as Red + per vehicle based route Colourisation change to Green from red if covered by the SW vehicle properly) and auto-flagging idle vehicles, supervisors will gain a clearer understanding of inactive versus active fleets with the following timing based validation as following: A. <5 min idle →on route B. 5–15 min idle → possibly delayed C. >15 min idle or at depot → stopped | Done
|  |  | 2. Define and Display 'Parking Zones' | Vehicles parked at depots or designated locations appear as if they are inactive or delayed. By defining parking zones (both the fixed or permanent parking areas and Temporary Parking areas/zones) and No parking zones (as 30 meter of patch from each turning point of turning radii of each urban road pattern) on the map with transparent overlays, the dashboard can intelligently distinguish between legitimate parking and unauthorized stoppages, reducing false alarms. | No data available for temporary parking zone. Already done for available parking zone
|  |  | 3. Enable Time-Based Color Transitions | Idle vehicles currently look the same regardless of how long they have been stationary. Introducing time-based color changes allows quick visual interpretation of whether stoppages are short delays, prolonged idling, or completed shifts. Implement time thresholds for color coding: A. <5 min idle → remain blue/brown (on route) B. 5–15 min idle → light orange (possibly delayed) C. >15 min idle or at depot → solid red (stopped) | Done
|  |  | 4. Add Tooltip or Info Card on Click | Vehicle icons currently show minimal information. Adding tooltips and info cards with details like last GPS timestamp, current status, and shift information will provide supervisors with actionable context directly from the dashboard. | Done- Add loader |  | Done- Add loader
|  |  | 5. Map Legend Enhancement | Legends are inconsistent across views. A standardized and dynamic legend system will ensure operators can interpret vehicle status, coverage, and alerts correctly without confusion. | Done
2 | Observation 2: | Observation 2.1 | 1. Unified Hierarchical Drill-Down Visualization | The dashboard is limited to high-level counts without spatial drill-down. Introducing a hierarchical visualization will allow progressive exploration from city-wide to vehicle-level. | pending | 4 sept | Divide the ward coverage in 2 section and disspaly ust below the parimandal 1 and 2 coverage
|  |  | 2. Enable Route Coverage Visualization | Missed or deviated routes are not easy to identify. Overlaying assigned versus actual route coverage on the live map will provide instant insight into operational compliance. | pending | 4 sept | part of map
|  |  | 3. Time-based Filters | The dashboard lacks shift-specific analysis. Adding time-based filters for first, second, and night shifts will enable precise monitoring of daily operations and productivity patterns. | Done- Based on WPP we have shown the progress.
|  |  | 4. Vehicle Utilization Summary Cards | Department officials cannot view overall utilization statistics quickly. Introducing summary cards for active, idle, and off-route vehicles provides a quick overview of fleet performance (Including the per vehicle based Shift records + Route to be coveror covered in the shift) | Done
|  | Observation 2.2 | 1. Integrate Mandal-wise View into Single Unified Dashboard | Operators must navigate separate screens for each mandal. Integrating them into a unified view with toggles and consistent legends will simplify use and reduce errors. | pending | 4 sept | Part of map implementation
|  |  | 2. Color Coding by Mandal with Status Overlay | The dashboard does not visually separate mandals clearly. Distinct colors for Pari Mandal 1 and Pari Mandal 2 with on/off route overlays will improve readability and reduce operator confusion. | Done | 4 sept
|  |  | 3. Legends & Labels | Legends and labels are inconsistent across layers. Standardizing the terminology and fixing label positions will improve usability. | Done | Parmandal Wise Color Coding
|  |  | 4. Pari Mandals on Map | Currently, pari mandal boundaries are not clearly drawn. Adding clear boundary polygons with labels will help supervisors relate performance data to geographies instantly. | need parimandal boundries
|  |  | 5. When a specific active route is clicked, it should show | When a route is selected, the dashboard should display route name, vehicle details, Area completed by vehicles (Shift or route covered by the vehicle)and live status. This ensures deeper visibility into operational execution on specific routes. | done |  |  | Add legends
|  | Observation 2.3 | 1. Enable Drill-down on the Map Itself | There is no ability to drill down from pari mandal to ward to vehicle within the same interface. Adding this functionality with consistent legends will provide clarity and ease of monitoring. | done |  |  | trf
|  |  | 2. Standardize Legend Naming | Legend terms differ across views, creating confusion. Using standardized terminology like 'On Route' and 'Off Route' ensures clarity for all operators. | Done |  |  | cloths
|  |  | 3. Dynamic Vehicle Clustering & Heatmap | Dense areas become cluttered with icons. Clustering vehicles and using heatmaps will improve visual clarity and help identify under-served areas. | pending- Heat map and single vehicles can not be shown at same time
|  |  | 4. Add Ward-Level Performance Metrics | Ward-level KPIs are not visible in the current dashboard. Displaying metrics like coverage percentage, active vehicles, and collection status per ward will strengthen micro-level monitoring. | Done
3 | Observation 3: | Observation 3.1 | 1. Use of GIS Layered Dashboard | Introduce a GIS-enabled layered dashboard that combines ward boundaries, routes, bins, and WPPs into one unified map view. This ensures real-time geospatial integration and enables supervisors to track operational progress across the entire city. | pending | 10 sept | Part of map
|  |  | 2. Add Route Coverage Layer | Add a route coverage layer that highlights completed, pending, and missed route segments in different colors. This improves accountability and helps detect service lapses instantly. | pending | 10 sept | Part of map
|  |  | 3. Overlay Wet & Dry Bin Locations | Currently, bins are not geospatially visible. Overlaying wet and dry bin layers with distinct symbols will allow monitoring of bin-level coverage and ensure no collection gaps go unnoticed. | pending | 10 sept | Part of map
|  |  | 4. Integrate WPP Layer | Integrating Waste Processing Plants (WPPs) into the dashboard with icons and facility details ensures that vehicle trips, bin assignments, and processing operations are transparently monitored and auditable. | Done- integrate don realtime map | 10 sept
|  | Observation 3.2 & 3.3 | 1. Enable Drill-Down by Admin Ward within Each Mandal | Enable map-based drill-down from mandal to ward and then to vehicle level. This hierarchical navigation provides supervisors with progressively detailed insights without switching dashboards. | done- Added hyperlinks as per instructions
|  |  | 2. Color-Coded Vehicle Status by Route in Map View | Introduce color-coded indicators for vehicles on routes, delayed, or completed. This instantly conveys the performance of each route and avoids misinterpretation of vehicle states. | pending | 10 sept | Part of map
|  |  | 3. Interactive Dashboard Cards | Add interactive dashboard cards showing KPIs such as active vehicles, bin coverage, and route completion. These should be clickable and linked to maps for quick drill-down analysis. | done
|  |  | 4. WPP Drill-Down Info | Enable WPP-level drill-down where users can click on a facility to see assigned vehicles, bin distribution, and real-time coverage statistics for better operational control. | done
4 | Observation 4 | 1. Legend Consistency and Standardization | I. Use uniform legend colors across all dashboard components | Standardize legend color codes across all dashboard views to ensure that route, bin, and vehicle data is always represented consistently, avoiding user confusion and improving clarity. | done
|  |  | II. Define and display these legends at a fixed and prominent location. | Legends should be placed at a fixed and prominent location on the dashboard so operators can quickly interpret the data without searching for visual references. | done
|  |  | III. Update the legend dynamically only when new data layers are added. | Legends must automatically adjust whenever new layers or datasets are added to the dashboard, ensuring that all data visualizations remain synchronized with their references. | done
|  | 2. Interactive Bar Chart Behavior | I. Ensure single-category responsiveness | Each bar chart interaction should only display data for the selected category, preventing unrelated visualizations from being triggered and keeping the user focus intact. | Done
|  |  | II. Enable independent bar interaction | Allow users to click bars independently so they can analyze multiple metrics without being forced into combined views, enabling granular exploration of operational data. | Done
5 | Observation 5 | 1. Incomplete Hourly Performance Justification | I. Link Percentage to Proof of Completion | Performance percentages should be backed by verifiable proof, such as GPS logs or route-level data, so supervisors can trust the completion statistics displayed in the dashboard. | Done
|  |  | II. Enable Route-Wise Performance Tables Provide a downloadable table/spreadsheet that | Provide downloadable spreadsheets or tables listing route-wise and ward-wise progress, including timestamps and bin-level details, for transparency and auditing. | Done
|  |  | III. Validation Logic | Clearly define and display the logic behind calculated percentages (e.g., bins covered vs. total bins), ensuring all performance figures are transparent and reproducible. | Done
|  | 2. Drill-Down Functionality Enhancement | I. Interactive Drill-Down from Bar Graphs | Enable users to drill down from high-level graphs into detailed ward, route, and bin-level information, making the dashboard more actionable for field operations. | done
|  |  | II. Hierarchical View | Provide a structured view where data can be navigated from city-wide to mandal, ward, route, and bin levels, ensuring supervisors get insights at every scale. | done
|  |  | III. Dynamic Time Filtering | Introduce time filters allowing users to analyze performance for specific shifts, days, or hours, supporting real-time and historical evaluations. | done
|  | 3. Dashboard Formatting & Design Consistency | I. Consistent Color Legends Across Visuals | Adopt a fixed set of color legends for all visuals—such as green for routes, blue for wet bins, and yellow for dry bins—to maintain uniformity across the platform. | Done
|  |  | II. Standardized Heading Style | Headings across the dashboard should follow a consistent font, size, and alignment style, giving the interface a professional and uniform appearance. | Done
|  |  | III. Add Tooltips and Legends on Graphs | Hover-enabled tooltips and inline legends on graphs will provide users with instant access to supporting statistics without cluttering the visualizations. | Done
| Observation 6 | 1. Hourly Data View with Interactive Trend Graph | Replace simple cumulative numbers with a line or bar chart showing | Replace static cumulative statistics with interactive trend graphs (line or bar) that show hourly dumping ground visits. This will allow supervisors to identify peak operational hours, monitor shifts in real-time, and compare performance across wards. | need api
|  | 2. Vehicle-Level Drilldown on Click (Drill Down) | When a user clicks on any value (e.g., “115 visits at 1100 AM”), the dashboard should open a popup or drilldown table showing | Enable drilldown functionality when clicking on aggregate data points. For example, clicking '115 visits at 11 AM' should open a detailed popup showing vehicle registration numbers, assigned wards, trip loads, and timestamps for full transparency. | need api
|  | 3. Integrate GPS Route History and Verification | I. For each listed vehicle | Integrate GPS route history playback per vehicle, allowing supervisors to verify that vehicles followed their assigned routes, did not skip bins, and reached designated facilities on time. | Done
|  | 4. Add Weight Analytics and Load Efficiency | 1. Show total and average load weight per vehicle and per ward. Identify | Introduce analytics for vehicle load efficiency by showing total and average weights carried per trip and per ward. This helps detect underutilized or overloaded vehicles, improving fleet management decisions. | need api
|  |  | 2. Sample KPIs to display | Add KPIs such as 'Average weight per trip', 'Maximum load today', and '% of vehicles under 60% capacity'. These metrics provide actionable insights into resource utilization and efficiency. | need api
|  | 5. Dashboard Filters for Better Navigation | Enable filters such as ▪Dumping Ground Location (if multiple) ▪Date & Time Range ▪Vehicle Type / ID ▪Shift (Morning, Afternoon, Night) ▪Ward or Admin Zone | Add interactive filters for parameters such as dumping ground location, date and time, vehicle type, ward, and shift. This allows managers to isolate and analyze specific operational slices effectively. | need api
|  | 6. Exportable Reports & Auto Summary | I. Allow users to download vehicle-wise dumping summary in Excel or PDF format. | Provide export functionality to generate Excel or PDF summaries of vehicle-wise dumping data, ensuring official record-keeping and compliance with reporting standards. | excel export is there
|  |  | II. Add a “Daily Summary Snapshot” showing | Add a daily auto-summary widget displaying total trips, tonnage dumped, average load per vehicle, and delayed trips. This enables supervisors to review key performance highlights quickly.
7 | Observation 7 | 1. Visual Emphasis on Key Metrics | ▪ Use bold font and larger text size for primary KPIs Example "On Route 32 Vehicles“ ▪ Supporting text (e.g., “Out of 35 assigned”) should be in a lighter or smaller font, maintaining focus on the primary number. | Redesign KPI cards so that critical numbers (e.g., '32 Vehicles On Route') appear in bold and larger font, while supporting text remains smaller. This improves focus on essential indicators. | Done
|  | 2. Color-Coded Highlights | I. Use colors to intuitively indicate performance status | Introduce intuitive color coding for KPIs: green for normal/on-time, orange for delayed, grey for inactive. This ensures immediate visual interpretation without reading text. | done
|  |  | II. Ensure that colors are consistent across all cards for quick interpretation. | Maintain consistent color usage across all KPI cards to prevent operator confusion and ensure that performance states are uniformly interpreted. | done
|  | 3. Dynamic Card Layout Based on Hierarchy | I.Arrange cards in a top-down hierarchy | Organize dashboard cards hierarchically (city → mandal → ward) with collapsible sections, enabling supervisors to drill down logically without cluttering the view. | done
|  | 4. Route Performance Indicators | I. Add a visual status bar or progress ring inside each card | Include progress bars or rings inside cards to visually represent route completion percentages. This provides at-a-glance clarity on progress levels. | done
|  | 5. Alerts and Flags for Late or Missed Routes | I. Include icon-based alert indicators | Introduce alert icons such as a red dot for late routes, a clock for pending starts, and a green check for completed routes. This creates a quick and intuitive alert mechanism for field supervisors. | pending | 3 sept | Add red and green icon for Route Timing Status
|  |  | II. Hover-over tooltips can display reason for delay or last GPS timestamp. | Add hover-tooltips on alerts to display supporting information, such as reasons for delays or last GPS update, providing context without extra clicks. | pending- There is no option to add reason for late. Also dont know whos responsibility to add those details | 3 sept
|  | 6. Geo-Linked Interactivity | ▪ Make the cards clickable, so selecting a card zooms the main map to that ward or vehicle route. ▪ This provides seamless integration between data and geography. | Enable geo-linked interactivity by making KPI cards clickable. When a card is selected, the dashboard should auto-zoom to the respective ward or vehicle route on the live map, ensuring seamless integration between numerical data and geography. | pending | 10 sept | Route Timing Status Show map in the popup with last location of the vehicles. And on right side show the list of vehicles already show in the modal . Just make sure that map will not reload every time
8 | Observation 8 |  | 1. Enable clickable features | Ensure that all dashboard map features such as bins, routes, vehicles, and WPPs are interactive. Clicking on any element should open real-time operational details in side panels, supporting quick field-level decision-making. | pending
|  |  | 2. Report Display Format | Adopt a clean, collapsible pop-up or right-panel display for clicked elements. This format should dynamically refresh with real-time GPS and IoT data, ensuring supervisors always see the latest information without system reloads. | pending
|  |  | 3. Ensure real-time refresh for data fields like current vehicle location, last collection time, etc. | Implement live data streaming into all info panels. Vehicle locations, collection timestamps, and trip status should update automatically in near real-time to support immediate operational responses. | done
|  |  | 1. Click on Bin Location (Wet/Dry Bin/Green Waste) Show Report Details | Enable bin-level drill down so that clicking on a wet, dry, or green waste bin displays its ID, type, last collection timestamp, assigned vehicle, and any missed collection history. This ensures accountability at the micro level of waste management. | done | 3 sept
9 | Observation 9 | 1. Align Legends in Map-Based Views and Geospatial Integrated | Legends in geospatial views should reflect the layer being viewed ▪ Routes = line color legend (e.g., green = completed, red = missed) ▪ Bins = dot color by type (e.g., wet/dry/overflowing) ▪ Vehicles = icon color based on status (e.g., on-time/idle/delayed) Display only relevant legends based on active layer or filter. | Standardize and align map legends with data layers being viewed. Routes should have line-based legends (green=completed, red=missed), WCP based bins should be represented by colored dots by type, and vehicles should use status-based icons for on-time, delayed, or idle states. | pending | 10 sept | Part of map
|  | 2. Align Legends in Map-Based Views | i. Each legend item must be dynamically linked to the correct data field in the backend. ii.Example If the user clicks on Turbhe, only data for Turbhe should load across ▪ Charts, Tables, Maps and KPI Cards | Ensure each legend item is directly connected to backend datasets. For example, clicking 'Turbhe' should filter results across maps, charts, and tables to display only Turbhe ward’s performance data. | pending | 10 sept | Part of map
|  | 3. Enable Interactive Legends | 1. Clicking on a legend item should act as a filter | Enable interactive legends so that selecting a legend item filters related map and chart layers. Hover-tooltips should also display supporting data like totals, contribution percentages, and last update timestamps for greater clarity. | pending | 10 sept
|  |  | 2. Tooltips should appear when hovering on a legend, showing ▪Total value ▪% contribution ▪Last update timestamp | This solution strengthens the ICCC dashboard by ensuring clarity, operational accountability, and real-time situational awareness without duplication of information across modules. | pending | 10 sept